# Weekly status report template

# Header

| Report week |  |
| --- | --- |
| Author / team |  |
| Recipients |  |
| Overall status |  |

# Body

| Summary |  |
| --- | --- |
| Accomplishments |  |
| Plan for next week |  |
| Risks and blockers |  |
| Decisions / help needed |  |
| Metrics |  |

# Tasks and progress

| Task | Owner | Status | Progress | Due |
| --- | --- | --- | --- | --- |

# Example — Weekly status report template

| Week | Week 43 · Oct 19–23, 2026 |
| --- | --- |
| Author | Maya Chen, Customer Success |
| Overall status | Amber: Delta Co migration two days late |
| Summary | 4 of 5 new accounts live; Acme renewed with 20% more seats. Delta's migration slipped to Oct 28 because their export arrived late. |
| Help needed | Approve a one-week extension for Delta's go-live by Tuesday. |

| Task | Owner | Status | Progress | Due |
| --- | --- | --- | --- | --- |
| Onboard 5 new accounts | Maya | On track | 4 of 5 | Oct 30 |
| Acme renewal | Sam | Done | Signed, +20% seats | Oct 22 |
| Delta Co data migration | Maya | At risk | 60% | Oct 28 |
| Q4 webinar content | Leo | On track | Draft ready | Nov 6 |

Workbami · https://workbami.com/templates/weekly-status-report/