## Weekly status report template
Weekly status report template
Header
Report week |  | The week covered, with dates.
Author / team |  | Who wrote it and for which team or project.
Recipients |  | Manager, stakeholders or client contacts.
Overall status |  | Green (on track), Amber (at risk) or Red (off track), with one reason.
Body
Summary |  | Two or three sentences: the most important result and the most important risk.
Accomplishments |  | Finished outcomes, with numbers where possible, not activities.
Plan for next week |  | Top 3–5 priorities with owners and dates.
Risks and blockers |  | What could derail the plan and what you are doing about it.
Decisions / help needed |  | Specific asks with a deadline.
Metrics |  | The 2–4 KPIs your team is measured on, with the trend.
Tasks and progress
Task | Owner | Status | Progress | Due
Workbami · https://workbami.com/templates/weekly-status-report/

## Example
Example — Weekly status report template
Week | Week 43 · Oct 19–23, 2026
Author | Maya Chen, Customer Success
Overall status | Amber: Delta Co migration two days late
Summary | 4 of 5 new accounts live; Acme renewed with 20% more seats. Delta's migration slipped to Oct 28 because their export arrived late.
Help needed | Approve a one-week extension for Delta's go-live by Tuesday.
Task | Owner | Status | Progress | Due
Onboard 5 new accounts | Maya | On track | 4 of 5 | Oct 30
Acme renewal | Sam | Done | Signed, +20% seats | Oct 22
Delta Co data migration | Maya | At risk | 60% | Oct 28
Q4 webinar content | Leo | On track | Draft ready | Nov 6